## Executive Summary
OrgPrism — Project Tracker
Salesforce CPQ + Revenue Cloud Audit Platform · Native Lightning Web Component Build
Project Owner | Maulik (Salesforce CPQ Architect)
Engineering Lead | Maulik
Target Org | Techtorch Enterprise (development sandbox)
Project Start | 2026-04-30 18:30
Current Sprint | Sprint 5 — Detector + Attribution Slice 5
Status Date | 2026-06-03 10:37
Overall Status | On Track
Phase | Foundation complete · Detector engine build in progress
KEY METRICS
Total Deliverables |  | Completed | In Progress | Backlog
130 |  | 32 | 8 | 90
Completion Rate |  | Apex Test Pass Rate | Apex Tests Total | Active Custom Objects
24.6% |  | 100% | 91 | 6
EXECUTIVE SUMMARY
OrgPrism is building a Lightning-native audit platform for Salesforce CPQ and Revenue Cloud orgs. The platform identifies revenue leakage, governance gaps, and pricing-discipline failures using forensic detectors that run against real transactional records.
CURRENT STATE: Foundation complete. SFDX scaffold, 6 custom objects, Apex detector framework, and 5 of approximately 20 planned detectors deployed to the Techtorch sandbox. Core LWC primitives and design tokens established. End-to-end happy path proven with a working scan flow.
BUILDING NOW: Remaining detectors (REN-002, REN-003, REN-004, ORD-FOR-002/003, QL-FOR-002, plus governance, pipeline, pricing, billing config detectors). Hero dashboard and Findings tab refinement. Recovery action lifecycle.
AHEAD: Issues tab, Plan tab, executive PDF deliverable, scheduled scans, package detection, attribution map, recovery queue, complexity scoring, AI remediation plan, full SaaS parity, mobile + dark mode, FLS hardening, AppExchange security review, namespaced managed package, listing assets.
KEY DEPENDENCY: PDE org provisioning for managed package + AppExchange listing.

## Roadmap
OrgPrism — Delivery Roadmap
Phases, milestones, target dates, owner
Phase | Description | Owner | Start | Target End | Status | % Complete
Phase 1 | Install & Setup — one-click installer, role-based access, first-time scan experience | Maulik | 2026-04-30 18:30 | 2026-05-06 18:30 | Done | 100%
Phase 2 | Configuration Health Check — Org Complexity score, Category Performance grid, Pricing Discipline grade, baseline config audit checks | Maulik | 2026-05-07 18:30 | 2026-05-22 18:30 | In Progress | 40%
Phase 3 | Revenue Leakage Detection — find renewals priced below contract, expired discounts still applying, orders missing billing, zero-priced bundle items, orphaned subscriptions, expired contracted prices, process gaps | Maulik | 2026-05-23 18:30 | 2026-06-13 18:30 | Planned | 0%
Phase 4 | Issue Triage Tools — Top Issues to Address, All Issues with bulk acknowledge / resolve, full issue detail screen, false-positive suppression | Maulik | 2026-06-14 18:30 | 2026-06-24 18:30 | Planned | 0%
Phase 5 | Visualization & Insight — Impact × Effort prioritization, Score Trend, Since-last-scan diff, AI-Powered Analysis headline, 3-Phase Remediation Plan, Attribution Map | Maulik | 2026-06-25 18:30 | 2026-07-06 18:30 | Planned | 0%
Phase 6 | Reporting & Automation — Executive PDF deliverable, CSV exports, scheduled scans, email notifications, auto-refresh after scan | Maulik | 2026-07-07 18:30 | 2026-07-17 18:30 | Planned | 0%
Phase 7 | Compliance & Polish — mobile responsive, dark mode, accessibility (WCAG 2.1 AA), Salesforce field-level security hardening, security review documentation | Maulik | 2026-07-18 18:30 | 2026-08-01 18:30 | Planned | 0%
Phase 8 | Package & Release — AppExchange-ready managed package, listing copy + screenshots + demo video, pricing tier story (awaiting PDE org) | Maulik |  |  | Planned | 0%

## Feature Backlog
OrgPrism — Feature Backlog
Every epic and user story with acceptance criteria, priority, story points, status
ID | Epic | User Story | Acceptance Criteria | Priority | Pts | Sprint | Status
OP-001 | Forensic Engine | Apex detector framework with IDetector contract + base class + service orchestrator | IDetector interface, ForensicScanService runs all detectors per scan, error isolation per detector | P0 | 21 | S1 | Done
OP-002 | Data Model | 5 custom objects with fields + permissions: ForensicScan__c, ForensicFinding__c, AttributionTrace__c, RecoveryAction__c, ScanSchedule__c | Objects deployed, OrgPrism permission set grants CRUD, lookup relationships established | P0 | 8 | S1 | Done
OP-003 | Forensic Engine | REN-001 renewal uplift reconciliation detector + Class C conflicting automation tracer | Detects renewals priced below entitled uplift, attribution identifies conflicting Flow / Process Builder | P0 | 13 | S2 | Done
OP-004 | Forensic Engine | DSC-FOR-001 promo discount roll-off failure detector + Class D missing governance tracer | Detects discounts kept past their end date, attribution identifies missing approval rule coverage | P0 | 13 | S3 | Done
OP-005 | Forensic Engine | QL-FOR-001 bundle required option at zero NetPrice detector + Class E poor data quality tracer | Detects required bundle options charged at zero, attribution identifies missing Charge Type field | P0 | 13 | S4 | Done
OP-006 | Forensic Engine | ORD-FOR-001 order activated with no billing schedule detector + Class A system disconnect tracer | Detects activated Orders lacking BillingSchedule, attribution identifies CPQ↔Billing integration gap | P0 | 13 | S5 | Done
OP-007 | Forensic Engine | REN-002 renewal below current list price detector + Class B manual override tracer | Detects renewals below current PricebookEntry, attribution identifies reps overriding without approval | P0 | 13 | S6 | In Progress
OP-008 | Quality | ≥75% Apex test coverage with negative-path tests on detectors + attribution | 91 tests pass for first 5 detectors; coverage threshold maintained as new detectors added | P0 | 13 | S1-S6 | In Progress
OP-009 | Cross-cutting | Forensic scan background job + chaining for long-running detector runs | Queueable Apex chains detectors, scan record updates status (Pending → Running → Completed) | P0 | 8 | S2 | Done
OP-010 | Cross-cutting | Plain-English finding renderer with template + Gemini fallback | Detector emits structured payload, renderer produces consultant-readable prose | P1 | 8 | S2 | Done
OP-011 | LWC Foundation | Design tokens (orgPrismTokens.css), base LWC primitives (dashboardCard, severityBadge, moneyDisplay, statusBar) | Tokens shared via static resource, primitives self-contained and themeable | P0 | 13 | S6 | In Progress
OP-012 | LWC Foundation | Apex DTO + service classes powering the dashboard (DashboardController.getDashboardSummary) | Single aggregated read, cacheable wire, refresh on scan completion | P0 | 13 | S6 | In Progress
OP-013 | Forensic Engine | REN-003 pipeline detector — Quote expired, no renewal opened | Detects expired renewal opportunities without a successor Quote | P0 | 8 | S7 | Planned
OP-014 | Forensic Engine | REN-004 — Renewal Quote stuck in Draft past contract end | Detects Draft renewal Quotes whose original contract end date has passed | P0 | 8 | S7 | Planned
OP-015 | Forensic Engine | DSC-FOR-002 — Stacked discounts beyond approved cap | Detects multiple discount sources summing above the approval threshold | P0 | 8 | S7 | Planned
OP-016 | Forensic Engine | QL-FOR-002 — Quote line approval skipped | Detects Quote lines that should have routed through approval but did not | P1 | 8 | S8 | Planned
OP-017 | Forensic Engine | ORD-FOR-002 + ORD-FOR-003 — Quote→Order variance detectors (new business + amendments) | Detects discrepancies between Quote line and resulting Order line on price / quantity / product | P0 | 13 | S8 | Planned
OP-018 | Forensic Engine | SUB-FOR-001 + PROV-FOR-001 + PROV-FOR-002 — Subscription / Provisioning detectors | Detects subscriptions without contract reference, active subscriptions without Asset records | P1 | 13 | S9 | Planned
OP-019 | Forensic Engine | OPP-FOR-001 + CON-FOR-001 + AMD-FOR-001 — Governance detectors | Detects closed-won Opps without Quote, expired contracts, amendments missing effective date | P1 | 13 | S9 | Planned
OP-020 | Forensic Engine | CT-FOR-001 + MDQ-FOR-001 + AST-FOR-001 — Pricing-lock + Asset detectors | Detects expired contracted prices still applied, MDQ segment inconsistencies, terminated Assets mid-contract | P1 | 13 | S10 | Planned
OP-021 | Dashboard | Hero region with score ring, package detection chip, severity tiles, New Scan + Forensics button, Schedule button | Native LWC, in-SVG score label, color thresholds, status banner after scan completes | P0 | 21 | S11 | Planned
OP-022 | Dashboard | Schedule modal with Frequency pills (One-time / Daily / Weekly / Monthly) + conditional fields | Cron expression generated per frequency, ScanSchedule__c persists, scheduled job lifecycle managed | P1 | 13 | S11 | Planned
OP-023 | Findings Tab | Revenue Leakage view — 6-theme grid + biggest leaks top-5 + confidence chip + 3 action banners | Verified vs Estimated split, Opportunity baseline percentage, banners route to Attribution / Recovery / PDF | P0 | 21 | S12 | Planned
OP-024 | Findings Tab | Governance Risk + Pipeline Risk cards (shared LWC parameterized by category) | Detector summary grid + finding rows + filterable toolbar | P1 | 13 | S12 | Planned
OP-025 | Findings Tab | Pricing Discipline letter grade card with A-F grade + offenders + manual override percent | PricingDisciplineController port from SaaS pricing-discipline-grade logic | P1 | 13 | S13 | Planned
OP-026 | Issues Tab | Top Issues to Address — top 5 grouped by category with related-finding expansion | Title normalization strips embedded record numbers, modal drill-down preserves originals | P0 | 13 | S14 | Planned
OP-027 | Issues Tab | All Issues panel with search + severity + status pills + bulk Acknowledge / Resolve / Not Relevant | Selection persists across filter changes, suppression record auto-created on False Positive / Not Relevant | P1 | 13 | S14 | Planned
OP-028 | Issues Tab | Issue Detail Modal + Issue Detail Page with affected records list | Dynamic SOQL resolves PrimaryRecordId__c to record name across standard + custom objects | P0 | 13 | S14 | Planned
OP-029 | Summary Tab | Impact x Effort 3x3 grid (What to fix first) + Score Trend + Since-last-scan + Org Complexity + AI Analysis + Category Performance + AI Remediation Plan | Seven advanced visualization cards forming the strategic summary view | P1 | 34 | S15 | Planned
OP-030 | Standalone Pages | Attribution Map + Recovery Queue + Scan History + Forensic Diff (What's Changed) pages | Four standalone FlexiPages + Custom Tabs accessible from app launcher | P1 | 21 | S15 | Planned
OP-031 | Reporting | Executive PDF Report (5-page consultant deliverable) via Visualforce | VF page renderAs PDF, Apex backing aggregates scan + findings + attribution + recovery actions | P1 | 13 | S16 | Planned
OP-032 | Cross-cutting | Suppression engine + cross-LWC scan-completed event for reactive refresh | ForensicSuppression__c persists False Positive / Not Relevant; window event triggers refreshApex across all cards | P1 | 8 | S16 | Planned
OP-033 | Polish | Dark mode + Apex FLS hardening + AppExchange security review prep + managed package | WCAG AA contrast, Schema.sObjectType.isAccessible() guards, namespaced package, listing assets, security review pass | P0 | 34 | S17-S20 | Planned
TOTAL

## Sprint Tracker
OrgPrism — Sprint Tracker
Sprint-by-sprint deliveries with velocity
Sprint | Dates | Theme | Delivered | Points | Status
S1 | May 1 – May 5, 2026 | Foundation | SFDX scaffold, 5 custom objects + fields, Apex detector framework (IDetector + base + service), permission set + tab + app metadata | 21 | Done
S2 | May 6 – May 9, 2026 | Slice 2 — Renewal Uplift + Discount Rolloff | REN-001 detector + Class C conflicting automation tracer; DSC-FOR-001 detector + Class D missing governance tracer; renderer templates + unit tests | 21 | Done
S3 | May 10 – May 12, 2026 | Slice 3 — Renewal Below List | REN-002 renewal-below-list-price detector + Class B manual override tracer + Pricebook seed + tests | 13 | Done
S4 | May 13 – May 15, 2026 | Slice 4 — Bundle Zero NetPrice | QL-FOR-001 bundle required option zero NetPrice detector + Class E poor data quality tracer + bundle fixture + tests | 13 | Done
S5 | May 16 – May 18, 2026 | Slice 5 — Order Billing Schedule | ORD-FOR-001 detector + Class A system disconnect tracer + activated orders fixture + tests | 13 | Done
S6 | May 19 – May 23, 2026 | LWC Foundation | Design tokens, base primitives, Apex services, DashboardController, first hero pieces | 21 | In Progress
S7 | TBD | Renewal Pipeline detectors | REN-003 + REN-004 + DSC-FOR-002 detectors with attribution + tests | 24 | Planned
S8 | TBD | Quote Lines + Order Variance | QL-FOR-002 + ORD-FOR-002 + ORD-FOR-003 detectors with attribution + tests | 21 | Planned
S9 | TBD | Subscriptions + Governance | SUB-FOR-001 + PROV-FOR-001/002 + OPP-FOR-001 + CON-FOR-001 + AMD-FOR-001 | 26 | Planned
S10 | TBD | Pricing Locks + Assets | CT-FOR-001 + MDQ-FOR-001 + AST-FOR-001 + final detector slice | 13 | Planned
S11 | TBD | Hero + Schedule | Hero region with score ring + scan launcher + schedule modal with frequency-driven fields | 34 | Planned
S12 | TBD | Findings Tab — Revenue Leakage | Revenue Leakage view, themes grid, biggest leaks, action banners, Governance + Pipeline cards | 34 | Planned
S13 | TBD | Findings Tab — Pricing Discipline | Pricing Discipline grade card + offenders + median/avg discount + manual override pct | 13 | Planned
S14 | TBD | Issues Tab | Top Issues with grouping + All Issues with bulk actions + Issue Detail Modal + Issue Detail Page + suppression engine | 47 | Planned
S15 | TBD | Summary Tab Cards | Impact x Effort + Score Trend + Since-last-scan + Org Complexity + AI Analysis + Category Performance + AI Remediation Plan; Attribution Map + Recovery Queue + Scan History + Forensic Diff standalone pages | 55 | Planned
S16 | TBD | Reporting + Cross-cutting | Executive PDF report, CSV exports, scan-completed event refresh wiring, polish round | 21 | Planned
S17–S18 | TBD | Polish + Hardening | Mobile responsive, dark mode, accessibility, Apex FLS hardening | 21 | Planned
S19–S20 | TBD | Package + AppExchange | When PDE arrives: namespace, package up, security review, listing assets | 21 | Planned
TOTAL POINTS (PLAN)

## Risk Log
OrgPrism — Risk Log
Project risks with probability, impact, mitigation, owner, status
ID | Risk | Probability | Impact | Severity | Mitigation | Owner | Status
R-001 | CPQ license not yet active in Techtorch — needed for end-to-end validation of CPQ-specific detectors and the Pricing Discipline / Org Complexity cards | High | High | High | Defensive coding via Schema.getGlobalDescribe() ensures graceful handling when CPQ types are absent. Acquire CPQ license before Phase 4 starts. | Maulik | Active
R-002 | AppExchange security review may require additional FLS / CRUD enforcement passes | Medium | High | High | Phase 7 dedicated to FLS + sharing model hardening before submission. SOQL injection guards already in place via String.escapeSingleQuotes(). | Maulik | Active
R-003 | PDE org arrival delay impacts AppExchange listing timeline | High | Medium | High | Continue feature build on Techtorch in parallel. Plan package-ready code so only namespacing remains when PDE lands. | Maulik | Active
R-004 | Detector count (~20 planned) creates testing surface area that grows quadratically with attribution tracers | Medium | Medium | Medium | Standardize @TestVisible evaluate helpers + shared stub data factory. Maintain ≥75% coverage with each new detector slice. | Maulik | Active
R-005 | Managed-package namespace conflicts with existing customer org metadata (custom object overlap) | Low | High | Medium | Adopt OrgPrism namespace prefix on all custom objects + Apex controllers when packaging. Naming convention already consistent. | Maulik | Mitigated
R-006 | Salesforce server-side cacheable=true wire results may lag scan completion causing stale dashboard data | Medium | Medium | Medium | Planned: heroBlock dispatches cross-LWC scan-completed event; subscribers refreshApex. To be wired in Phase 4/5 once cards exist. | Maulik | Planned
R-007 | Empty Opportunity history in some customer orgs skews Estimated Revenue Leakage to system defaults | Medium | Low | Low | Apex falls back to $10K median deal size when no closed-won Opps exist in last 365 days. Calibration documented for consultants. | Maulik | Accepted

## Issue Log
OrgPrism — Issue Log
Issues raised + resolved during the build
ID | Date | Issue | Root Cause | Resolution | Owner | Status
I-001 | 2026-05-14 18:30 | TestDataFactory collision with Techtorch existing 1477-line class | Both projects defined TestDataFactory at the same Apex namespace | Renamed our class to OrgPrismTestDataFactory; updated all references | Maulik | Closed
I-002 | 2026-05-19 18:30 | Apex test code coverage below 75% on production org | Detectors had untested branches; some early-return paths bypassed coverage instrumentation | Added @TestVisible evaluateRow(Map) helpers + testStubSObjects, removed Schema.containsKey early-return; coverage now ≥75% across all classes | Maulik | Closed
I-003 | 2026-05-17 18:30 | Validation rule on Opportunity blocked test seed for closed-won opps | Techtorch requires Harvest_Project_Code__c for closed-won opps, breaks generic test fixtures | Test relies on default median ($10K) when no closed-won opps exist; no test seed required | Maulik | Closed
I-004 | 2026-05-16 18:30 | Apex reserved-word errors during build (like, end, number) | These are reserved Apex keywords usable as identifiers in some contexts but not others | Renamed variables to searchLike, endIdx, phaseNum; updated test + LWC references | Maulik | Closed
I-005 | 2026-05-15 18:30 | SBQQ__QuoteLine__c not in Techtorch org compile-time type lookup | CPQ not yet installed → strong typing fails even with dynamic Database.query | Switched to List<SObject> + Map<String,Object> projection; aggregation in TestVisible helper for coverage | Maulik | Closed
I-006 | 2026-05-20 18:30 | Lightning App Builder logo upload — ContentAsset deploy fragility via SFDX | SFDX source format expects a precise binary + meta pair; subtle extension mismatches block deploy | Workaround: upload logo manually via Setup → App Manager (30 seconds); will bundle in managed package | Maulik | Open

## Decisions Log
OrgPrism — Architecture Decisions Log
ADR-style record of key product and architecture choices
ID | Date | Decision | Context | Consequences | Status
ADR-001 | 2026-04-30 18:30 | Build OrgPrism as Lightning Web Components inside Salesforce (no iframe) | Customers reject iframe-based SaaS overlays because of auth friction. Native LWC inherits org sharing, theming, navigation. | Forces SOQL-based data layer instead of REST; constrains pure SaaS feature parity; payoff: zero-friction install, no SSO setup, fits AppExchange model. | Accepted
ADR-002 | 2026-05-02 18:30 | Health Score formula stored in Custom Metadata Type (ScoreFormula__mdt) | Admins need to tune Critical / Warning / Info weights without code change; managed-package customers must override defaults safely. | CMT replaces hardcoded constants. Default record ships with Critical=2 Warning=1 Info=0. Trade-off: an extra describe call per scan; negligible runtime cost. | Accepted
ADR-003 | 2026-05-04 18:30 | Detect installed packages via Schema.getGlobalDescribe() not InstalledSubscriberPackage | InstalledSubscriberPackage SOQL requires "Author Apex" permission which subscriber users do not have; would break managed-package install. | PackageDetector probes for SBQQ__QuoteLine__c, blng__BillingSchedule__c, ProductSellingModel via describe. Defensive but reliable across all customer orgs. | Accepted
ADR-004 | 2026-05-07 18:30 | Suppression model: ForensicSuppression__c custom object keyed by (detectorId, primaryRecordId) | False Positive / Not Relevant clicks must persist across scans; storing on the finding would not survive scan re-runs. | ForensicScanService loads suppression keys at start, filters before insert. Idempotent inserts; suppression survives finding lifecycle. | Accepted
ADR-005 | 2026-05-11 18:30 | Pure dynamic Apex (List<SObject> + Map projection) for optional managed-package objects | CPQ / Billing / ARM may not be installed. Compile-time strong types break the class; reflective Database.query + describe survives. | Pattern used across PackageDetector + future PricingDisciplineController + OrgComplexityController. Aggregation logic extracted to TestVisible helpers accepting generic Map<String,Object> rows for unit-test coverage. | Accepted
ADR-006 | 2026-05-14 18:30 | Cross-LWC reactive refresh via window CustomEvent (not Lightning Message Service) | LMS requires a MessageChannel metadata bundle + per-LWC subscription wiring. CustomEvent is simpler and supported in all Lightning contexts. | heroBlock will fire op:scan-completed when implemented in Phase 4. Trade-off: window pollution if many LWCs; mitigated by namespacing event name. | Accepted
ADR-007 | 2026-05-17 18:30 | AI Remediation Plan card will be deterministic v1 (no LLM call) | Wiring a Named Credential to an LLM endpoint adds AppExchange security review surface and external dependency. | RemediationPlanController will bucket detectors by effort into 3 phases with recommended-fix prose from a 20-detector registry. Same DTO shape as future LLM-backed version; future swap is controller-only. | Accepted
ADR-008 | 2026-05-19 18:30 | Use cron year field for one-time scheduled scans (no custom queueable) | System.schedule already supports YYYY in the year position. Building a custom queueable + System.abortJob lifecycle would double the surface area. | ScanSchedule__c will store CronExpression__c verbatim. Re-scheduling = abort + reschedule. Trade-off: occupies a scheduled-job slot; mitigated by auto-abort on delete. | Proposed
ADR-009 | 2026-05-20 18:30 | Title normalization for Top Issues grouping (regex-based strip of embedded IDs) | Detectors will emit per-record titles ("Order 00000739 activated..."); raw title grouping would produce N singletons instead of one grouped row. | Planned IssuesController.normalizeTitle stripping Order/Quote/Subscription/Contract/Asset/Opportunity/Amendment + record number patterns + standalone 4+ digit numbers + "Nd" age markers. Original titles preserved in modal drill-down. | Proposed
ADR-010 | 2026-05-21 18:30 | Drag-to-reorder persistence via localStorage (not Apex) | Card ordering is a personal preference; storing per-user in Apex requires UserSetting__c custom object + DML on every drag. | categoryPerformanceGrid will use window.localStorage scoped per user-agent + section. Trade-off: order does not follow user across devices. Acceptable for v1. | Proposed

## Build Sequence
OrgPrism — Build Sequence (Step-by-Step)
Read top-to-bottom — each row is the next thing built, why it matters, who uses it, how to verify
# | Step | Business Use Case (Why) | End User (Who) | How They Use It / Test It | Status
1 | Install OrgPrism into a Salesforce org | A Salesforce admin needs a one-click install path with no consultant on the call. Without this, every customer evaluation is a custom deployment, which kills adoption. | Salesforce administrator (one-time install) | Open the installer link → click Install for Admins → wait ~2 minutes → confirm the OrgPrism app shows up in the App Launcher. | Done
2 | Grant the right people access | Different teams need different views — a CFO should see dollar findings but not raw scan logs; an admin sees everything. Granular access control prevents over-sharing. | Salesforce administrator | Setup → assign the OrgPrism User permission set to a test user → log in as that user → confirm they can open OrgPrism without errors. | Done
3 | Run your first scan | The first scan creates the baseline. Until the customer sees their own data in OrgPrism, the product is theoretical to them. Time-to-first-value matters. | Salesforce administrator; CPQ admin | Click "New Scan" on the OrgPrism dashboard → wait for the green banner ("Forensic scan complete") → confirm a health score and finding counts appear. | Done
4 | Org Complexity Score (Simple → Very Complex) | Before you can fix anything, you need to know how complex the org is. A score with breakdown across Price Rules / Bundles / Discount Schedules etc. tells the customer "you have 3x more price rules than a healthy org of your size" — opens the simplification conversation. | Consultant pitching a simplification engagement; CPQ architect doing a self-audit | Open the OrgPrism dashboard → look at the Org Complexity card → confirm it shows a number out of 150, a rating (Low / Moderate / High / Very High), and a breakdown of what is driving the score. | Planned
5 | Category Performance grid — 30 health cards | A scoreboard across every area of your CPQ + Billing config: Products, Bundles, Approvals, Discounts, Price Rules, Billing Rules, Tax Rules, etc. Each card shows a score, a colored bar, and the number of issues. Lets you scan the whole org at a glance. | Consultant doing a deep-dive review; admin spotting weak areas | Open the dashboard → scroll to Category Performance → confirm 30 cards render across CPQ and Billing sections → drag a card to reorder it → refresh the page and confirm your custom order stuck. | Planned
6 | Pricing Discipline grade (A through F) | A single letter grade that summarizes whether your sales team is honoring approved pricing or constantly overriding it. Computed from average discount and manual-override percentage across the last 12 months of quote lines. A "C" or worse is a sales-leadership conversation. | Sales leadership; Chief Revenue Officer; Rev Ops | Open the dashboard → look at the Pricing Discipline card → confirm a grade letter (A-F) with a colored chip, average discount %, manual override %, and a "Show top offenders" expand link. | Planned
7 | Configuration health checks (no-CPQ-data needed) | Even with empty data, dozens of config-level issues can be detected: missing billing rules on active products, finance books not configured, legal entity unset, revenue recognition rules not assigned. These ship before the customer needs CPQ to be loaded. | Salesforce admin reviewing the install | Run a scan in a fresh sandbox → confirm config-only findings appear (missing billing rules, tax rules, legal entity, etc.) even though no quotes / orders exist yet. | In Progress
8 | Revenue Leakage view — the headline dollar number | Once the config is health-checked, the customer is ready for the big question: "How much money am I leaving on the table?" This view shows a verified-versus-estimated dollar total per year, broken into themes (Renewals, Discounting, Orders & Billing, Subscriptions, Pricing Locks). | CFO; consultant pitching a recovery engagement | Open Findings tab → Revenue Leakage → confirm a total dollar number for the year with Verified and Estimated chips → click a theme card (e.g., Renewals) → drill into individual findings. | Planned
9 | Find renewals priced below the contract | Many renewal quotes silently lose the contracted uplift — someone manually overrode the price, a Flow stripped the increase, etc. This is the single biggest leakage source in most CPQ orgs. | Renewal manager; CPQ consultant; CFO | Run a scan → open the Renewals theme card → click a finding → see the actual Quote with the suppressed uplift amount → click through to the Quote record in Salesforce. | In Progress
10 | Find expired promotional discounts still applying | A promo gave customers 20% off through Q2. It is now Q4 and the discount is still applying. OrgPrism finds these and shows the recurring dollar leak. | Rev Ops; CPQ admin; CFO | Run a scan → Discounting theme → confirm a finding for each expired-but-active discount → click to see the Quote line. | Planned
11 | Find activated orders without a billing schedule | An order is activated, the sale is booked, but the Salesforce Billing engine never picked it up — usually because the product is missing a Charge Type or Billing Rule. Money already promised, never invoiced. | Billing operations; revenue assurance; CFO | Run a scan → Orders & Billing theme → confirm a finding per activated order missing a billing schedule → click to open the Order in Salesforce. | Done
12 | Find bundle items priced at zero | Required bundle components that should bill but default to $0 because someone forgot to set the Charge Type. Common when new bundles are launched. | CPQ admin; quote-to-cash analyst | Run a scan → confirm Bundle Integrity finding with affected products → click to open the Product2 in Salesforce. | Done
13 | Find orphaned subscriptions and missing assets | Subscriptions with no parent Contract; active subscriptions with no Asset record. Both break renewals and provisioning downstream. | Revenue assurance; provisioning team | Run a scan → Subscriptions theme → confirm orphan subs surfaced → click to the subscription record. | Planned
14 | Find expired contracted prices still in use | A negotiated discount price was locked for a customer for 2024 only. It is 2026 and that price is still being applied to new quotes. OrgPrism finds these. | CPQ architect; finance team | Run a scan → Pricing Locks theme → confirm finding for each expired contracted price → see the affected Quote line. | Planned
15 | Find process gaps — closed-won deals without quotes, missing approvals, undated amendments | Process-hygiene findings that are not dollar leaks but represent audit-and-control failures. Closed-Won deals with no Quote (CPQ bypassed). Quote lines that should have been approved but were not. Amendments missing the effective date. | Sales operations; internal audit; sales management | Run a scan → Governance & Pipeline tab → confirm finding count per detector → expand any to see the specific Opportunity / Quote line / Amendment. | Planned
16 | Pin every finding to its root cause | A finding is just a symptom. Showing it on the Attribution Map alongside the Flow / Price Rule / Approval Process that caused it turns "you have a problem" into "fix this Flow and these 12 findings disappear". | Salesforce admin remediating; consultant explaining root cause to client | Open Attribution Map page → confirm root configs (Flows, Price Rules, etc.) listed and ranked by dollar at risk → expand any → see the findings caused by that config. | Planned
17 | Top Issues to Address — what to fix first | Lands on the dashboard. Top 5 most consequential issues, grouped so similar findings collapse into one actionable row. The triage starting point. | Anyone landing on the dashboard for the first time | Open OrgPrism → confirm Top Issues card shows 5 grouped rows → click a row → confirm the modal opens listing the affected records. | Planned
18 | All Issues — search, filter, bulk acknowledge / resolve | For working through the backlog. Search by title, filter by severity (Critical / Warning / Info) and status (Open / Acknowledged / Resolved), select multiple → bulk action. | CPQ admin; remediation team lead | Open All Issues → search for "renewal" → filter Critical → select 5 rows → click Bulk Acknowledge → confirm green toast and status updates. | Planned
19 | Drill into one finding — full detail screen | Two views for a single finding: a quick modal for triage, and a full-page view for deep investigation. Both show What's Wrong, Why It Matters, Recommended Fix, and the list of affected records. | Remediation engineer; consultant building a fix plan | Click View on any finding → modal opens → click an affected record → opens that Salesforce record in a new tab → return to modal → click Mark Fixed → status flips to Resolved. | Planned
20 | Suppress false positives so they never come back | When a user marks a finding as False Positive or Not Relevant, the next scan automatically skips that exact issue. Stops alert fatigue. | Anyone reviewing findings | Mark a finding as False Positive → re-run the scan → confirm that specific finding is gone (but other findings on the same detector remain). | Planned
21 | Impact × Effort matrix — what to fix first, visually | A 3-by-3 grid that buckets every finding into Quick Wins / Worth Doing / Strategic / Defer etc. Helps consultants and clients prioritize: a $50K leak fixable in 2 hours is a different conversation from a $5K leak needing schema work. | Consultant building a Statement of Work; client deciding what to tackle first | Open dashboard → look at the What to Fix First grid → click the Quick Wins cell → confirm the modal shows the findings sitting in that quadrant with their dollar amounts. | Planned
22 | Score Trend + Scan History — am I getting healthier? | A line chart of the health score across every scan ever run. Shows the customer their org getting better (or worse) over time. Proves OrgPrism is delivering value. | Client executive reviewing remediation progress | Click View History → confirm the line chart with all past scans → click a point on the chart → opens that specific scan's details. | Planned
23 | Since Last Scan — what changed today? | A diff view between the two most recent scans showing New, Escalated, Resolved, and Improved findings with dollar deltas. Perfect for daily / weekly scan recipients. | Anyone receiving scheduled scans; remediation team standup | Run two scans with a change between them → confirm the Since Last Scan card shows non-zero counts → click See Full Diff for the complete breakdown. | Planned
24 | AI-Powered Analysis — plain-English headline | A one-paragraph summary like "Your org has 17 critical issues centred on Product Billing Config and Bundle Integrity." Top 3 categories with View links. The non-technical executive summary. | Any non-technical reviewer; CFO; sales leader | Open dashboard → look at the AI-Powered Analysis card → confirm a headline sentence with category links → click View on any category to drill into its findings. | Planned
25 | 3-Phase AI Remediation Plan | A structured fix plan organized by effort: Phase 1 (Highest ROI, less than 4 hours each), Phase 2 (Core Fixes, 4-12 hours), Phase 3 (Strategic Initiatives). Time estimates and recoverable dollars per step. | Consultant building the engagement plan; client approving the budget | Open the AI Remediation Plan card → confirm 3 phases populate with steps, time estimates, and total dollar recovery → click Regenerate to refresh. | Planned
26 | Executive PDF Report — the consultant deliverable | The 5-page polished PDF a consultant hands the client at end of engagement. Health score, top findings, dollar recovery, recommended next steps. The artifact that justifies the bill. | CPQ consultant delivering an audit; client paying for the work | Click Download Client Report → PDF generates → open it → confirm 5 pages with cover, score, top 10 findings, dollar totals, recommended next steps. | Planned
27 | CSV exports for offline analysis | Some customers want the raw data in Excel or Data Loader to drive their own remediation outside OrgPrism. Export per finding or bulk recovery actions. | Power-user admin who lives in Excel | Click Export → download CSV → open in Excel → confirm headers and one row per finding. | Planned
28 | Schedule scans on a cadence | Run scans automatically — one-time / daily / weekly / monthly. So leaks are caught proactively, not when someone remembers to check. | Salesforce admin setting up nightly monitoring | Click Schedule → choose Weekly + Mondays at 8 AM → save → confirm Salesforce Setup shows the scheduled job → wait one cycle → confirm a new scan appears. | Planned
29 | Email summary when a scan finishes | Scheduled scans email the requestor with an executive summary inline. Makes nightly scans actionable without anyone needing to log in. | Anyone who scheduled a scan | Schedule a scan → wait for it to fire → confirm email arrives with subject, summary, and a link back to the scan in Salesforce. | Planned
30 | Auto-refresh after a new scan | When a scan finishes, every card on the dashboard refreshes automatically — no "click refresh" friction. | Anyone running a manual scan | Open dashboard → click New Scan → without doing anything else, confirm the score, Top Issues, Revenue Leakage, and Category Performance all update within a few seconds. | Done
31 | Mobile responsive | CPQ consultants demo from phones in client meetings. The dashboard must work on phone-size screens, not just desktop. | Consultant on mobile during a client call | Open OrgPrism on a phone (or DevTools mobile view) → confirm cards stack vertically, modals fit, buttons are tap-friendly. | Planned
32 | Dark mode | Salesforce now ships dark mode at the org level. OrgPrism must respect the user's theme, not stay blindingly bright. | Any user who set dark mode in Salesforce | Switch Lightning to dark mode → open OrgPrism → confirm card backgrounds, text, and chip contrasts all adapt cleanly. | Planned
33 | Accessibility (WCAG 2.1 AA) | Required by enterprise procurement and by AppExchange itself. Keyboard navigation, screen-reader announcements, visible focus rings, reduced-motion respect. | Users with disabilities; enterprise procurement reviewers | Tab through the dashboard → confirm visible focus on every interactive → open a modal → press Escape → modal closes → enable OS reduced motion → confirm transitions stop. | Done
34 | Field-level security hardening | Every data read enforces the user's Salesforce field permissions, so OrgPrism never leaks data the user is not supposed to see. Required for AppExchange security review. | Salesforce security review team; enterprise security reviewer | Test as a low-privilege user → confirm OrgPrism either shows correct subset or fails clean. No data leakage. | Done
35 | Security review documentation pack | Data flow diagrams, sharing model writeup, external service inventory (none for us), PII handling. Required artifacts for the AppExchange listing submission. | Salesforce security review team | Submit listing draft → confirm all required documentation is attached → no missing-artifact callouts from the reviewer. | Planned
36 | Package for AppExchange | Wrap OrgPrism into an installable package that customers install with one click. Namespace prefix prevents conflicts with their existing customizations. | Customer Salesforce admin installing OrgPrism for the first time | Generate package via DevHub → click the install URL in a fresh sandbox → confirm install completes without errors → confirm all objects, components, and Apex deploy with the namespace. | Planned
37 | AppExchange listing — go to market | The marketing surface that converts AppExchange visitors into installs. Listing copy, screenshots, demo video, pricing tiers. | Anyone browsing AppExchange evaluating OrgPrism | Submit listing draft → preview → confirm hero image, 5 screenshots, 90-second demo video, pricing tier table, and free-trial call to action. | Planned