## Executive Summary
OrgPrism — Project Tracker
Salesforce CPQ + Revenue Cloud Audit Platform · Native Lightning Web Component Build
Project Owner | Maulik (Salesforce CPQ Architect)
Engineering Lead | Maulik
Target Org | Techtorch Enterprise (development sandbox)
Project Start | 2026-04-30 18:30
Current Sprint | Sprint 5 — Detector + Attribution Slice 5
Status Date | 2026-06-03 07:31
Overall Status | On Track
Phase | Foundation complete · Detector engine build in progress
KEY METRICS
Total Deliverables |  | Completed | In Progress | Backlog
130 |  | 32 | 8 | 90
Completion Rate |  | Apex Test Pass Rate | Apex Tests Total | Active Custom Objects
24.6% |  | 100% |  | 6
EXECUTIVE SUMMARY
OrgPrism is building a Lightning-native audit platform for Salesforce CPQ and Revenue Cloud orgs. The platform identifies revenue leakage, governance gaps, and pricing-discipline failures using forensic detectors that run against real transactional records.
CURRENT STATE: Foundation complete. SFDX scaffold, 6 custom objects, Apex detector framework, and 5 of approximately 20 planned detectors deployed to the Techtorch sandbox. Core LWC primitives and design tokens established. End-to-end happy path proven with a working scan flow.
BUILDING NOW: Remaining detectors (REN-002, REN-003, REN-004, ORD-FOR-002/003, QL-FOR-002, plus governance, pipeline, pricing, billing config detectors). Hero dashboard and Findings tab refinement. Recovery action lifecycle.
AHEAD: Issues tab, Plan tab, executive PDF deliverable, scheduled scans, package detection, attribution map, recovery queue, complexity scoring, AI remediation plan, full SaaS parity, mobile + dark mode, FLS hardening, AppExchange security review, namespaced managed package, listing assets.
KEY DEPENDENCY: PDE org provisioning for managed package + AppExchange listing.

## Roadmap
OrgPrism — Delivery Roadmap
Phases, milestones, target dates, owner
Phase | Description | Owner | Start | Target End | Status | % Complete
Phase 0 | SFDX scaffold, custom objects, permission set, detector framework | Maulik | 2026-04-30 18:30 | 2026-05-06 18:30 | Done | 100%
Phase 1 | Detector engine — first 5 detectors (REN-001, DSC-FOR-001, QL-FOR-001, ORD-FOR-001) + attribution tracers | Maulik | 2026-05-07 18:30 | 2026-05-17 18:30 | Done | 100%
Phase 2 | LWC foundation — design tokens, base primitives, Apex services | Maulik | 2026-05-18 18:30 | 2026-05-22 18:30 | In Progress | 60%
Phase 3 | Detector engine — remaining 15 detectors across renewals, governance, pipeline, billing, discounting | Maulik | 2026-05-23 18:30 | 2026-06-13 18:30 | Planned | 0%
Phase 4 | Hero + Summary tab + Findings tab (Revenue Leakage, Governance, Pipeline, Pricing) | Maulik | 2026-06-14 18:30 | 2026-06-27 18:30 | Planned | 0%
Phase 5 | Issues tab + Plan tab + Cross-cutting (Export, PDF report, Schedule) | Maulik | 2026-06-28 18:30 | 2026-07-11 18:30 | Planned | 0%
Phase 6 | Polish — mobile, dark mode, accessibility, AppExchange readiness | Maulik | 2026-07-12 18:30 | 2026-07-20 18:30 | Planned | 0%
Phase 7 | Apex FLS hardening + AppExchange security review prep | Maulik | 2026-07-21 18:30 | 2026-08-04 18:30 | Planned | 0%
Phase 8 | Managed package + AppExchange listing (awaiting PDE org) | Maulik |  |  | Planned | 0%

## Feature Backlog
OrgPrism — Feature Backlog
Every epic and user story with acceptance criteria, priority, story points, status
ID | Epic | User Story | Acceptance Criteria | Priority | Pts | Sprint | Status
OP-001 | Forensic Engine | Apex detector framework with IDetector contract + base class + service orchestrator | IDetector interface, ForensicScanService runs all detectors per scan, error isolation per detector | P0 | 21 | S1 | Done
OP-002 | Data Model | 5 custom objects with fields + permissions: ForensicScan__c, ForensicFinding__c, AttributionTrace__c, RecoveryAction__c, ScanSchedule__c | Objects deployed, OrgPrism permission set grants CRUD, lookup relationships established | P0 | 8 | S1 | Done
OP-003 | Forensic Engine | REN-001 renewal uplift reconciliation detector + Class C conflicting automation tracer | Detects renewals priced below entitled uplift, attribution identifies conflicting Flow / Process Builder | P0 | 13 | S2 | Done
OP-004 | Forensic Engine | DSC-FOR-001 promo discount roll-off failure detector + Class D missing governance tracer | Detects discounts kept past their end date, attribution identifies missing approval rule coverage | P0 | 13 | S3 | Done
OP-005 | Forensic Engine | QL-FOR-001 bundle required option at zero NetPrice detector + Class E poor data quality tracer | Detects required bundle options charged at zero, attribution identifies missing Charge Type field | P0 | 13 | S4 | Done
OP-006 | Forensic Engine | ORD-FOR-001 order activated with no billing schedule detector + Class A system disconnect tracer | Detects activated Orders lacking BillingSchedule, attribution identifies CPQ↔Billing integration gap | P0 | 13 | S5 | Done
OP-007 | Forensic Engine | REN-002 renewal below current list price detector + Class B manual override tracer | Detects renewals below current PricebookEntry, attribution identifies reps overriding without approval | P0 | 13 | S6 | In Progress
OP-008 | Quality | ≥75% Apex test coverage with negative-path tests on detectors + attribution | 91 tests pass for first 5 detectors; coverage threshold maintained as new detectors added | P0 | 13 | S1-S6 | In Progress
OP-009 | Cross-cutting | Forensic scan background job + chaining for long-running detector runs | Queueable Apex chains detectors, scan record updates status (Pending → Running → Completed) | P0 | 8 | S2 | Done
OP-010 | Cross-cutting | Plain-English finding renderer with template + Gemini fallback | Detector emits structured payload, renderer produces consultant-readable prose | P1 | 8 | S2 | Done
OP-011 | LWC Foundation | Design tokens (orgPrismTokens.css), base LWC primitives (dashboardCard, severityBadge, moneyDisplay, statusBar) | Tokens shared via static resource, primitives self-contained and themeable | P0 | 13 | S6 | In Progress
OP-012 | LWC Foundation | Apex DTO + service classes powering the dashboard (DashboardController.getDashboardSummary) | Single aggregated read, cacheable wire, refresh on scan completion | P0 | 13 | S6 | In Progress
OP-013 | Forensic Engine | REN-003 pipeline detector — Quote expired, no renewal opened | Detects expired renewal opportunities without a successor Quote | P0 | 8 | S7 | Planned
OP-014 | Forensic Engine | REN-004 — Renewal Quote stuck in Draft past contract end | Detects Draft renewal Quotes whose original contract end date has passed | P0 | 8 | S7 | Planned
OP-015 | Forensic Engine | DSC-FOR-002 — Stacked discounts beyond approved cap | Detects multiple discount sources summing above the approval threshold | P0 | 8 | S7 | Planned
OP-016 | Forensic Engine | QL-FOR-002 — Quote line approval skipped | Detects Quote lines that should have routed through approval but did not | P1 | 8 | S8 | Planned
OP-017 | Forensic Engine | ORD-FOR-002 + ORD-FOR-003 — Quote→Order variance detectors (new business + amendments) | Detects discrepancies between Quote line and resulting Order line on price / quantity / product | P0 | 13 | S8 | Planned
OP-018 | Forensic Engine | SUB-FOR-001 + PROV-FOR-001 + PROV-FOR-002 — Subscription / Provisioning detectors | Detects subscriptions without contract reference, active subscriptions without Asset records | P1 | 13 | S9 | Planned
OP-019 | Forensic Engine | OPP-FOR-001 + CON-FOR-001 + AMD-FOR-001 — Governance detectors | Detects closed-won Opps without Quote, expired contracts, amendments missing effective date | P1 | 13 | S9 | Planned
OP-020 | Forensic Engine | CT-FOR-001 + MDQ-FOR-001 + AST-FOR-001 — Pricing-lock + Asset detectors | Detects expired contracted prices still applied, MDQ segment inconsistencies, terminated Assets mid-contract | P1 | 13 | S10 | Planned
OP-021 | Dashboard | Hero region with score ring, package detection chip, severity tiles, New Scan + Forensics button, Schedule button | Native LWC, in-SVG score label, color thresholds, status banner after scan completes | P0 | 21 | S11 | Planned
OP-022 | Dashboard | Schedule modal with Frequency pills (One-time / Daily / Weekly / Monthly) + conditional fields | Cron expression generated per frequency, ScanSchedule__c persists, scheduled job lifecycle managed | P1 | 13 | S11 | Planned
OP-023 | Findings Tab | Revenue Leakage view — 6-theme grid + biggest leaks top-5 + confidence chip + 3 action banners | Verified vs Estimated split, Opportunity baseline percentage, banners route to Attribution / Recovery / PDF | P0 | 21 | S12 | Planned
OP-024 | Findings Tab | Governance Risk + Pipeline Risk cards (shared LWC parameterized by category) | Detector summary grid + finding rows + filterable toolbar | P1 | 13 | S12 | Planned
OP-025 | Findings Tab | Pricing Discipline letter grade card with A-F grade + offenders + manual override percent | PricingDisciplineController port from SaaS pricing-discipline-grade logic | P1 | 13 | S13 | Planned
OP-026 | Issues Tab | Top Issues to Address — top 5 grouped by category with related-finding expansion | Title normalization strips embedded record numbers, modal drill-down preserves originals | P0 | 13 | S14 | Planned
OP-027 | Issues Tab | All Issues panel with search + severity + status pills + bulk Acknowledge / Resolve / Not Relevant | Selection persists across filter changes, suppression record auto-created on False Positive / Not Relevant | P1 | 13 | S14 | Planned
OP-028 | Issues Tab | Issue Detail Modal + Issue Detail Page with affected records list | Dynamic SOQL resolves PrimaryRecordId__c to record name across standard + custom objects | P0 | 13 | S14 | Planned
OP-029 | Summary Tab | Impact x Effort 3x3 grid (What to fix first) + Score Trend + Since-last-scan + Org Complexity + AI Analysis + Category Performance + AI Remediation Plan | Seven advanced visualization cards forming the strategic summary view | P1 | 34 | S15 | Planned
OP-030 | Standalone Pages | Attribution Map + Recovery Queue + Scan History + Forensic Diff (What's Changed) pages | Four standalone FlexiPages + Custom Tabs accessible from app launcher | P1 | 21 | S15 | Planned
OP-031 | Reporting | Executive PDF Report (5-page consultant deliverable) via Visualforce | VF page renderAs PDF, Apex backing aggregates scan + findings + attribution + recovery actions | P1 | 13 | S16 | Planned
OP-032 | Cross-cutting | Suppression engine + cross-LWC scan-completed event for reactive refresh | ForensicSuppression__c persists False Positive / Not Relevant; window event triggers refreshApex across all cards | P1 | 8 | S16 | Planned
OP-033 | Polish | Dark mode + Apex FLS hardening + AppExchange security review prep + managed package | WCAG AA contrast, Schema.sObjectType.isAccessible() guards, namespaced package, listing assets, security review pass | P0 | 34 | S17-S20 | Planned
|  |  |  | TOTAL | 463

## Sprint Tracker
OrgPrism — Sprint Tracker
Sprint-by-sprint deliveries with velocity
Sprint | Dates | Theme | Delivered | Points | Status
S1 | June 1,2026 | Foundation | SFDX scaffold, 5 custom objects + fields, Apex detector framework (IDetector + base + service), permission set + tab + app metadata | 21 | Done
S2 | TBD | Slice 2 — Renewal Uplift + Discount Rolloff | REN-001 detector + Class C conflicting automation tracer; DSC-FOR-001 detector + Class D missing governance tracer; renderer templates + unit tests | 21 | Done
S3 | TBD | Slice 3 — Renewal Below List | REN-002 renewal-below-list-price detector + Class B manual override tracer + Pricebook seed + tests | 13 | Done
S4 | TBD | Slice 4 — Bundle Zero NetPrice | QL-FOR-001 bundle required option zero NetPrice detector + Class E poor data quality tracer + bundle fixture + tests | 13 | Done
S5 | TBD | Slice 5 — Order Billing Schedule | ORD-FOR-001 detector + Class A system disconnect tracer + activated orders fixture + tests | 13 | Done
S6 | TBD | LWC Foundation | Design tokens, base primitives, Apex services, DashboardController, first hero pieces | 21 | In Progress
S7 | TBD | Renewal Pipeline detectors | REN-003 + REN-004 + DSC-FOR-002 detectors with attribution + tests | 24 | Planned
S8 | TBD | Quote Lines + Order Variance | QL-FOR-002 + ORD-FOR-002 + ORD-FOR-003 detectors with attribution + tests | 21 | Planned
S9 | TBD | Subscriptions + Governance | SUB-FOR-001 + PROV-FOR-001/002 + OPP-FOR-001 + CON-FOR-001 + AMD-FOR-001 | 26 | Planned
S10 | TBD | Pricing Locks + Assets | CT-FOR-001 + MDQ-FOR-001 + AST-FOR-001 + final detector slice | 13 | Planned
S11 | TBD | Hero + Schedule | Hero region with score ring + scan launcher + schedule modal with frequency-driven fields | 34 | Planned
S12 | TBD | Findings Tab — Revenue Leakage | Revenue Leakage view, themes grid, biggest leaks, action banners, Governance + Pipeline cards | 34 | Planned
S13 | TBD | Findings Tab — Pricing Discipline | Pricing Discipline grade card + offenders + median/avg discount + manual override pct | 13 | Planned
S14 | TBD | Issues Tab | Top Issues with grouping + All Issues with bulk actions + Issue Detail Modal + Issue Detail Page + suppression engine | 47 | Planned
S15 | TBD | Summary Tab Cards | Impact x Effort + Score Trend + Since-last-scan + Org Complexity + AI Analysis + Category Performance + AI Remediation Plan; Attribution Map + Recovery Queue + Scan History + Forensic Diff standalone pages | 55 | Planned
S16 | TBD | Reporting + Cross-cutting | Executive PDF report, CSV exports, scan-completed event refresh wiring, polish round | 21 | Planned
S17–S18 | TBD | Polish + Hardening | Mobile responsive, dark mode, accessibility, Apex FLS hardening | 21 | Planned
S19–S20 | TBD | Package + AppExchange | When PDE arrives: namespace, package up, security review, listing assets | 21 | Planned
|  |  | TOTAL POINTS (PLAN) | 432

## Risk Log
OrgPrism — Risk Log
Project risks with probability, impact, mitigation, owner, status
ID | Risk | Probability | Impact | Severity | Mitigation | Owner | Status
R-001 | CPQ license not yet active in Techtorch — needed for end-to-end validation of CPQ-specific detectors and the Pricing Discipline / Org Complexity cards | High | High | High | Defensive coding via Schema.getGlobalDescribe() ensures graceful handling when CPQ types are absent. Acquire CPQ license before Phase 4 starts. | Maulik | Active
R-002 | AppExchange security review may require additional FLS / CRUD enforcement passes | Medium | High | High | Phase 7 dedicated to FLS + sharing model hardening before submission. SOQL injection guards already in place via String.escapeSingleQuotes(). | Maulik | Active
R-003 | PDE org arrival delay impacts AppExchange listing timeline | High | Medium | High | Continue feature build on Techtorch in parallel. Plan package-ready code so only namespacing remains when PDE lands. | Maulik | Active
R-004 | Detector count (~20 planned) creates testing surface area that grows quadratically with attribution tracers | Medium | Medium | Medium | Standardize @TestVisible evaluate helpers + shared stub data factory. Maintain ≥75% coverage with each new detector slice. | Maulik | Active
R-005 | Managed-package namespace conflicts with existing customer org metadata (custom object overlap) | Low | High | Medium | Adopt OrgPrism namespace prefix on all custom objects + Apex controllers when packaging. Naming convention already consistent. | Maulik | Mitigated
R-006 | Salesforce server-side cacheable=true wire results may lag scan completion causing stale dashboard data | Medium | Medium | Medium | Planned: heroBlock dispatches cross-LWC scan-completed event; subscribers refreshApex. To be wired in Phase 4/5 once cards exist. | Maulik | Planned
R-007 | Empty Opportunity history in some customer orgs skews Estimated Revenue Leakage to system defaults | Medium | Low | Low | Apex falls back to $10K median deal size when no closed-won Opps exist in last 365 days. Calibration documented for consultants. | Maulik | Accepted